## Overview
P2 ¦ Repair & Reserve Planner
EXAMPLE - all property figures and evidence are hypothetical. Version 1.0 ¦ USD ¦ en-US
MODELED amounts and dates. This calendar is a funding test, not an inspection or lifespan forecast.
Property / version | BIRCH-01 / v2-D1
Model start / selected cost case | Nov 2026 / Base
Immediate work ¦ selected case | 5000
Recurring maintenance ¦ annual, transfer to P1 | 1200
Future replacement payments ¦ 24 months | 14400
Replacement reserve at start | 13500
Separate operating cash ¦ excluded from calendar | 4000
Monthly replacement contribution | 250
Chosen minimum replacement floor | 2500
Lowest replacement balance, incl. start | 2500
First month below floor ¦0 means start | NONE
Required starting reserve at planned contribution | 13500
Top-up from original reserve | 6000
Monthly needed if original reserve kept | 1750
Original monthly contribution feasibility | EXCEEDS stated monthly cash
Current start funding status | AT / ABOVE required start; verify funding
Original calendar low ¦ original starting cash | -3500
Current calendar end ¦ month 24 | 5100
Handoff to P1: immediate work, annual recurring maintenance, replacement start and monthly contribution each retain their own labels. Copy property ID, source version, as-of date and model start. P2 replacement $13,500 is NOT P1 total reserves $17,500. The $6,000 top-up is not a second expense.

## Settings
P2 ¦ Reserve settings
EXAMPLE - all property figures and evidence are hypothetical. Version 1.0 ¦ USD ¦ en-US
Property ID | BIRCH-01
Analysis version | v2-D1
Analysis / evidence date | 2026-10-03
Calendar begins | 2026-11-01
Selected cost case | Base
Replacement reserve at start | 13500
Minimum replacement reserve floor | 2500
Monthly replacement contribution | 250
Monthly operating cash BEFORE contribution | 579.6509
Original replacement reserve | 7500
Initial top-up funding source | $6,000 from uncommitted property capital; total budget 85000.
Source / assumption for settings | Hypothetical Birch reserve case in the book. Monthly cash here is stabilized, not the delay year.
State of settings | Scenario
Operating cash account ¦ excluded here | 4000
Only replacement cash enters this calendar. v2-D1 replacement $13,500 + separate operating $4,000 = total initial reserves $17,500. P1 commitment $83,000. The two-month delay requires the dated operating bridge in the book; stabilized $579.65/month cannot fund bills before rent arrives.

## Work items
P2 ¦ Work scope and evidence
EXAMPLE - all property figures and evidence are hypothetical. Version 1.0 ¦ USD ¦ en-US
Active? | Component ID | Category | Scope / observed condition | Low USD | Base USD | High USD | Extra contingency | Payment month | State | Source / assumption | Evidence date | Timing basis | Owner | Unresolved question | Validation / funded cost
Active | SAFETY | Immediate | Electrical safety scope; separate from interior work. | 1200 | 1500 | 2000 | 25% | 0 | Scenario | Authored hypothetical Birch work allowance, not a real contractor quote. | 2026-10-03 | Before occupancy; hypothetical contractor schedule. | Buyer | Obtain current inspection and written scope before commitment. | 1875
Active | INTERIOR | Immediate | Paint and flooring; no roof or water-heater scope. | 2000 | 2500 | 3500 | 25% | 0 | Scenario | Authored hypothetical Birch work allowance, not a real contractor quote. | 2026-10-03 | Before occupancy; hypothetical contractor schedule. | Buyer | Obtain current inspection and written scope before commitment. | 3125
Active | ROOF | Replacement | Full roof replacement; no roof work in initial scope. | 9000 | 10000 | 12500 | 20% | 4 | Scenario | Authored hypothetical Birch work allowance, not a real contractor quote. | 2026-10-03 | Month 4 payment after contribution; hypothetical specialist assessment. | Buyer | Obtain current inspection and written scope before commitment. | 12000
Active | HEATER | Replacement | Replace water heater; no initial heater work. | 1500 | 2000 | 2500 | 20% | 18 | Scenario | Authored hypothetical Birch work allowance, not a real contractor quote. | 2026-10-03 | Month 18 payment after contribution; hypothetical specialist assessment. | Buyer | Obtain current inspection and written scope before commitment. | 2400
Active | MAINTENANCE | Recurring maintenance | Routine annual upkeep; excludes initial scopes and scheduled replacements. | 1000 | 1200 | 1800 | 0% | 0 | Scenario | Authored hypothetical Birch work allowance, not a real contractor quote. | 2026-10-03 | Annual allowance paid through operating cash; no extra contingency included. | Buyer | Obtain current inspection and written scope before commitment. | 1200
Inactive | [8 empty] | Unknown | [5 empty] | INACTIVE
Inactive | [8 empty] | Unknown | [5 empty] | INACTIVE
Inactive | [8 empty] | Unknown | [5 empty] | INACTIVE
Inactive | [8 empty] | Unknown | [5 empty] | INACTIVE
Inactive | [8 empty] | Unknown | [5 empty] | INACTIVE
Inactive | [8 empty] | Unknown | [5 empty] | INACTIVE
Inactive | [8 empty] | Unknown | [5 empty] | INACTIVE
Use unique IDs for distinct scopes. A repeated active ID remains pending until you separate or reconcile the overlapping work. Recurring maintenance amounts are annual; they transfer to P1, not replacement withdrawals. Additional contingency 0 is appropriate only when your source already includes it; explain this in the source.

## Calendar
P2 ¦ Replacement cash calendar
EXAMPLE - all property figures and evidence are hypothetical. Version 1.0 ¦ USD ¦ en-US
Contribution enters at month end BEFORE scheduled payment. Month 0 tests the starting floor. Separate operating cash is excluded. Dates are planning assumptions until supported.
Month | Payment date | Opening cash | Contribution | Payment | Closing cash
0 | 2026-11-01 |  |  |  | 13500
1 | 2026-11-30 | 13500 | 250 | 0 | 13750
2 | 2026-12-31 | 13750 | 250 | 0 | 14000
3 | 2027-01-31 | 14000 | 250 | 0 | 14250
4 | 2027-02-28 | 14250 | 250 | 12000 | 2500
5 | 2027-03-31 | 2500 | 250 | 0 | 2750
6 | 2027-04-30 | 2750 | 250 | 0 | 3000
7 | 2027-05-31 | 3000 | 250 | 0 | 3250
8 | 2027-06-30 | 3250 | 250 | 0 | 3500
9 | 2027-07-31 | 3500 | 250 | 0 | 3750
10 | 2027-08-31 | 3750 | 250 | 0 | 4000
11 | 2027-09-30 | 4000 | 250 | 0 | 4250
12 | 2027-10-31 | 4250 | 250 | 0 | 4500
13 | 2027-11-30 | 4500 | 250 | 0 | 4750
14 | 2027-12-31 | 4750 | 250 | 0 | 5000
15 | 2028-01-31 | 5000 | 250 | 0 | 5250
16 | 2028-02-29 | 5250 | 250 | 0 | 5500
17 | 2028-03-31 | 5500 | 250 | 0 | 5750
18 | 2028-04-30 | 5750 | 250 | 2400 | 3600
19 | 2028-05-31 | 3600 | 250 | 0 | 3850
20 | 2028-06-30 | 3850 | 250 | 0 | 4100
21 | 2028-07-31 | 4100 | 250 | 0 | 4350
22 | 2028-08-31 | 4350 | 250 | 0 | 4600
23 | 2028-09-30 | 4600 | 250 | 0 | 4850
24 | 2028-10-31 | 4850 | 250 | 0 | 5100

## Work summary
P2 ¦ Work record
EXAMPLE - all property figures and evidence are hypothetical. Version 1.0 ¦ USD ¦ en-US
Component / category | Funded cost | Scope and timing
SAFETY / Immediate | 1875 | Electrical safety scope; separate from interior work. ¦ Before occupancy; hypothetical contractor schedule.
INTERIOR / Immediate | 3125 | Paint and flooring; no roof or water-heater scope. ¦ Before occupancy; hypothetical contractor schedule.
ROOF / Replacement | 12000 | Full roof replacement; no roof work in initial scope. ¦ Month 4 payment after contribution; hypothetical specialist assessment.
HEATER / Replacement | 2400 | Replace water heater; no initial heater work. ¦ Month 18 payment after contribution; hypothetical specialist assessment.
MAINTENANCE / Recurring maintenance | 1200 | Routine annual upkeep; excludes initial scopes and scheduled replacements. ¦ Annual allowance paid through operating cash; no extra contingency included.
Unused | INACTIVE
Unused | INACTIVE
Unused | INACTIVE
Unused | INACTIVE
Unused | INACTIVE
Unused | INACTIVE
Unused | INACTIVE

## Calculations
P2 ¦ Inspectable requirements
EXAMPLE - all property figures and evidence are hypothetical. Version 1.0 ¦ USD ¦ en-US
Month | Cumulative payments | Required starting cash | Monthly from original
1 | 0 | 2500 | 0
2 | 0 | 2500 | 0
3 | 0 | 2500 | 0
4 | 12000 | 13500 | 1750
5 | 12000 | 13250 | 1400
6 | 12000 | 13000 | 1166.6667
7 | 12000 | 12750 | 1000
8 | 12000 | 12500 | 875
9 | 12000 | 12250 | 777.7778
10 | 12000 | 12000 | 700
11 | 12000 | 11750 | 636.3636
12 | 12000 | 11500 | 583.3333
13 | 12000 | 11250 | 538.4615
14 | 12000 | 11000 | 500
15 | 12000 | 10750 | 466.6667
16 | 12000 | 10500 | 437.5
17 | 12000 | 10250 | 411.7647
18 | 14400 | 12400 | 522.2222
19 | 14400 | 12150 | 494.7368
20 | 14400 | 11900 | 470
21 | 14400 | 11650 | 447.619
22 | 14400 | 11400 | 427.2727
23 | 14400 | 11150 | 408.6957
24 | 14400 | 10900 | 391.6667

## Guide
P2 ¦ Repair & Reserve Planner
EXAMPLE - all property figures and evidence are hypothetical. Version 1.0 ¦ USD ¦ en-US
Set the account and dates
Settings describes replacement funds only, the floor you choose, contribution and start date. The24-month calendar pays at month end after contribution. Earlier actual due dates require your own dated bridge. Funding sources must be named; future operating cash cannot arrive early.
Enter real scopes
Activate work rows; give each distinct scope a unique component ID. Immediate work is paid from the acquisition budget. Recurring maintenance is an annual operating cost to transfer to P1. Replacements withdraw from the reserve calendar. Never charge the same roof twice.
Choose costs without hiding gaps
Base needs only Base cost; missing optional Low/High does not block it. Each active selected cost requires a state, meaningful source, evidence date, timing explanation and owner. Unknown stays pending. Duplicate active IDs require scope reconciliation. Inactive rows do not block outputs.
Read the timing test
Overview compares starting funds and contributions with dated payments and your floor. Start below the floor fails at month 0. Required start cannot be computed when a replacement cost/date is missing. The known immediate-work total remains usable when a roof quote is pending.
Use the Birch example
Corrected replacement start $13,500 keeps $2,500 at month 4 and ends $5,100 at month 24. Original $7,500 falls to -$3,500 at month 4. Keeping it would require $1,750/month, above stabilized operating cash $579.65. The chosen $6,000 top-up comes from initial property capital.
Transfer by label
Birch v2-D1 also holds $4,000 operating cash outside P2; P1 has $17,500 total initial reserves and $83,000 initial commitment. Manual transfer records must preserve account scope and version. XLSX calculates; PDFs are static. Save personal copies and compare written evidence before deciding.